## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Setup project structure and Springboot Configuration. | MUST HAVE | NA | T.Kalpanashree,S.Sujitha, Duggirala Druhitha | 3- Completed
Sprint 1 | Sprint 1 | US-02 | Create base backend package structure for bank simulator | MUST HAVE | US-01 | T.Kalpanashree,S.Sujitha, Duggirala Druhitha | 3- Completed
Sprint 1 | Sprint 1 | US-03 | Implement Account class and repository with balance class | MUST HAVE | US-02 | T.Kalpanashree,S.Sujitha, Duggirala Druhitha | 3- Completed
Sprint 1 | Sprint 1 | US-04 | Implement account creation API | MUST HAVE | US-03 | T.Kalpanashree,S.Sujitha, Duggirala Druhitha | 3- Completed
Sprint 1 | Sprint 1 | US-05 | Configure application properties and server settings | MUST HAVE | US-01 | T.Kalpanashree,S.Sujitha, Duggirala Druhitha | 3- Completed
Sprint 1 | Sprint 1 | US-06 | Test REST APIs using Postman tool | SHOULD HAVE | US-04 | T.Kalpanashree,S.Sujitha, Duggirala Druhitha | 3- Completed
Sprint 2 | Sprint 2 | US-07 | Implement deposit functionality module | MUST HAVE | US-04 | T.Kalpanashree, ,S.Sujitha, Duggirala Druhitha | 3- Completed
Sprint 2 | Sprint 2 | US-08 | Implement withdrawal functionality module with exception handling | MUST HAVE | US-07 | T.Kalpanashree, S. Sujitha, Duggirala Druhitha | 3- Completed
Sprint 2 | Sprint 2 | US-09 | Implement transfer functionality modules between the accounts | MUST HAVE | US-08 | T.Kalpanashree, S.Sujitha, Duggirala Druhitha | 3- Completed
Sprint 2 | Sprint 2 | US-10 | Implement account details module | SHOULD HAVE | US-04 | T.Kalpanashree,,S.Sujitha, Duggirala Druhitha | 3- Completed
Sprint 3 | Sprint 3 | US-11 | Implement transaction history module | SHOULD HAVE | US-07 | T.Kalpanashree, S.Sujitha, Duggirala Druhitha | 3- Completed
Sprint 3 | Sprint 3 | US-12 | Create basic HTML page for banking simulator | COULD HAVE | US-04 | T.Kalpanashree,,S.Sujitha, Duggirala Druhitha | 3- Completed
Sprint 3 | Sprint 3 | US-13 | Add CSS styling for frontend layout | COULD HAVE | US-12 | T.Kalpanashree,,S.Sujitha, Duggirala Druhitha | 3- Completed
Sprint 4 | Sprint 4 | US-14 | Add JavaScript for the frontend design | COULD HAVE | US-12 | T.Kalpanashree,S.Sujitha, Duggirala Druhitha | 3- Completed
Sprint 4 | Sprint 4 | UA-15 | Perform basic testing and verification of project structure | MUST HAVE | US-09, US-11 | T.Kalpanashree, S.Sujitha, Duggirala Druhitha | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 74 | 8 | 10 | 10 | 5 | 4 | 4 | 6 | 6 | 7 | 4 | 2 | 3 | 4 | 3
SPRINT 1 BACKLOG
US-01 | T1 | Java revision(OOPs concept, Collections, Exception handling) | 2025-12-04 | 2025-12-04 | T.Kalpanashree,S.Sujitha, Duggirala Druhitha | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T2 | Project Setup & Github Repository Initialization | 2025-12-05 | 2025-12-05 | T.Kalpanashree,S.Sujitha, Duggirala Druhitha | Others | 3-Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T3 | Springboot setup and configuration | 2025-12-08 | 2025-12-08 | T.Kalpanashree,S.Sujitha, Duggirala Druhitha | Others | 3-Completed | 4 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T4 | Create base package structure | 2025-12-10 | 2025-12-10 | T. Kalpanashree,S.Sujitha, Duggirala Druhitha | Coding | 3-Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T5 | Create Account class | 2025-12-12 | 2025-12-12 | T. Kalpanashree,S.Sujitha, Duggirala Druhitha | Coding | 3-Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T6 | Create Balance class | 2025-12-15 | 2025-12-15 | T. Kalpanashree,S.Sujitha, Duggirala Druhitha | Coding | 3-Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T7 | Create Account Repository | 2025-12-17 | 2025-12-17 | T. Kalpanashree,S.Sujitha, Duggirala Druhitha | Coding | 3-Completed | 3 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T8 | Implement Account Creation API | 2025-12-19 | 2025-12-22 | T. Kalpanashree, Duggirala Druhitha,S.Sujitha | Coding | 3-Completed | 6 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
US-05 | T9 | Configure application.properties | 2025-12-24 | 2025-12-24 | T. Kalpanashree,S.Sujitha, Duggirala Druhitha | Coding | 3-Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T10 | Implement Deposit Module | 2025-12-26 | 2025-12-29 | T. Kalpanashree, ,S.Sujitha, Duggirala Druhitha | Coding | 3-Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
US-08 | T11 | Implement Withdraw Module + Exceptions | 2025-12-31 | 2026-01-02 | T. Kalpanashree, S.Sujitha, Duggirala Druhitha | Coding | 3-Completed | 7 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1
US-09 | T12 | Implement Transfer Module | 2026-01-03 | 2026-01-05 | T. Kalpanashree, S.Sujitha, Duggirala Druhitha | Coding | 3-Completed | 8 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
US-10 | T13 | Implement Account Details API | 2026-01-06 | 2026-01-06 | T. Kalpanashree,S.Sujitha, Duggirala Druhitha | Coding | 3-Completed | 4 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-11 | T14 | Implement Transaction History Module | 2026-01-07 | 2026-01-08 | T. Kalpanashree, S.Sujitha, Duggirala Druhitha | Coding | 3-Completed | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
US-12 | T15 | Create Basic HTML Page | 2026-01-09 | 2026-01-09 | T. Kalpanashree,,S.Sujitha, Duggirala Druhitha | Coding | 3-Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
US-13 | T16 | Add CSS Styling | 2026-01-12 | 2026-01-12 | T. Kalpanashree,S.Sujitha, Duggirala Druhitha | Coding | 3-Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
US-14 | T17 | Add JavaScript for frontend | 2026-01-14 | 2026-01-15 | T. Kalpanashree,S.Sujitha, Duggirala Druhitha | Coding | 3-Completed | 4 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-15 | T18 | Final Testing & Verification | 2026-01-16 | 2026-01-20 | T. Kalpanashree,S. Sujitha, Duggirala Druhitha | Testing | 3-Completed | 5 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Revised Java concepts and practiced small programs | Revised Java concepts and practiced small programs
Sprint 1 | Day 2 | GitHub repository setup confusion | Watched documentation and successfully configured repository
Sprint 1 | Day 3 | Spring Boot dependency and version conflict | Fixed pom.xml and reloaded Maven dependencies
Sprint 1 | Day 4 | Server port already in use error | Changed server port in application.properties
Sprint 1 | Day 5 | Confusion in designing package structure | Referred standard Spring Boot project structure
Sprint 1 | Day 6 | API returning 404 error | Fixed controller mapping and base URL
Sprint 1 | Day 7 | JSON request/response format issue | Validated request body and fixed DTO mapping
Sprint 2 | Day 1 | Error in deposit logic due to null balance object | Added proper object initialization and null checks
Sprint 2 | Day 2 | Withdrawal exception not handled properly | Implemented custom exception and try-catch block
Sprint 2 | Day 3 | Transfer API failed due to transaction consistency issue | Implemented validation and rollback logic
Sprint 2 | Day 4 | Account details API returned incomplete data | Fixed entity mapping and response structure
Sprint 2 | Day 5 | Transaction history list not sorted | Added sorting logic by date
Sprint 2 | Day 6 | Postman tests failing for some edge cases | Fixed validation logic and added boundary checks
Sprint 3 | Day 1 | HTML page layout looked broken | Fixed basic structure and div alignment
Sprint 3 | Day 2 | CSS not applying properly | Fixed file linking and path issues
Sprint 3 | Day 3 | JavaScript button actions not working | Fixed DOM loading issue and function binding
Sprint 3 | Day 4 | UI not properly calling backend APIs | Fixed CORS configuration and API URLs
Sprint 4 | Day 1 | Some APIs failed during final testing | Debugged and fixed logical errors
Sprint 4 | Day 2 | Inconsistent data in transaction history | Fixed database update sequence
Sprint 4 | Day 3 | Minor UI and validation bugs | Performed bug fixing and retesting
Sprint 4 | Day 4 | Project documentation formatting issue | Corrected document structure and screenshots

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-12-04 | 2025-12-24 | T. Kalpanashree,S.Sujitha, Duggirala Druhitha | Planning taks before implementation | Starting coding without design | Using checklist before development | Prepared proper task plan for Sprint 2
2 | Sprint 2 | 2025-12-26 | 2026-01-06 | T. Kalpanashree, Duggirala Druhitha, S.Sujitha | Writing validations and test cases | Ignoring edge cases | Testing APIs using Postman | Added validation and exception handling
3 | Sprint 3 | 2026-01-07 | 2026-01-13 | T. Kalpanashree, Duggirala Druhitha, S.Sujitha | Designing UI before implementation | Making last-minute UI changes | Incremental UI improvement | Prepared basic UI layout before coding
4 | Sprint 4 | 2026-01-14 | 2026-01-20 | T. Kalpanashree, Duggirala Druhitha, S.Sujitha | Performing full regression testing | Delaying documentation | Updating documentation regularly | Final testing and report completed